## Sheet1
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New estimates of effort remaining at end of | [6 empty] | Status
[6 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
[6 empty] | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19
US001 | As a passenger, I want to be able to self register into the system with my details. | Task 1 | Siddharth | Design the UI for Registration. | 4 | 2021-06-13: 4; 2021-06-14: 1; 2021-06-15: 0 | Closed
|  | Task 2 | Aditya | Write a program to serve the Registration page. | 2 | 2021-06-13: 2; 2021-06-14: 0 | Closed
|  | Task 3 | Siddharth | Design and create DB fields for Registration. | 2 | 2021-06-13: 2; 2021-06-14: 0 | Closed
|  | Task 4 | Aditya | Create fields to capture passenger details. | 3 | 2021-06-13: 3; 2021-06-14: 3; 2021-06-15: 0 | Closed
|  | Task 5 | Aditya | Capture passenger details and store in a collection. | 2 | 2021-06-13: 2; 2021-06-14: 2; 2021-06-15: 0 | Closed
|  | Task 6 | Aditya | Generate seven digit random ID. | 3 | 2021-06-13: 3; 2021-06-14: 3; 2021-06-15: 3; 2021-06-16: 0 | Closed
|  | Task 7 | Aditya | Display passenger ID in UI. | 3 | 2021-06-13: 3; 2021-06-14: 3; 2021-06-15: 3; 2021-06-16: 0 | Closed
|  | Task 8 | Aditya | Insert Passenger Details into DB. | 3 | 3 | 3 | 3 | 3 | 0 |  |  | Closed
|  | Task 9 | Aditya | Display "Registration Successful" message in console. | 2 | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 10 | Aditya | Display passenger Id, name, email after Registration. | 3 | 3 | 3 | 3 | 3 | 3 |  |  | Closed
US002 | As a passenger, I want to be able to login to the system and book ticket for a journey. | Task1 | Siddharth | Design and create DB fields for Ticket Booking. | 2 | 2021-06-13: 2; 2021-06-14: 2; 2021-06-15: 0 | Closed
|  | Task 2 | Siddharth | Design the UI for Login. | 3 | 3 | 3 | 3 | 3 | 0 |  |  | Closed
|  | Task 3 | Siddharth | Implement input validation for Login. | 4 | 4 | 4 | 4 | 4 | 0 |  |  | Closed
|  | Task 4 | Siddharth | Design and create DB fields for master data. | 2 | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 5 | Aditya | Write a program to login to the system. | 4 | 4 | 4 | 4 | 4 | 4 | 0 |  | Closed
|  | Task 6 | Aditya | Create fields to capture booking details. | 3 | 3 | 3 | 3 | 3 | 3 | 0 |  | Closed
|  | Task 7 | Siddharth | Design UI for Passenger Home Page. | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 8 | Siddharth | Design UI for Ticket Booking Page. | 3 | 3 | 3 | 3 | 3 | 3 | 0 |  | Closed
|  | Task 9 | Siddharth | Implement input validation for Ticket Booking form. | 3 | 3 | 3 | 3 | 3 | 3 | 0 |  | Closed
US003 | As a passenger, I want to be able to login to the system and view the booked ticket history. | Task 1 | Siddharth | Design and create DB fields for Booking List. | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Closed
|  | Task 2 | Siddharth | Design the UI for Booked History Page. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  | Task 3 | Aditya | Insert Ticket details in to DB. | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Closed
|  | Task 4 | Aditya | Display PNR, Date, Source, Destination after booking. | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Closed
|  | Task 5 | Aditya | Write a program to display booked history in tables. | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Closed
|  | Task 6 | Aditya | Implement Pagination in booked history page. | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Closed